## quickquery
ID | Summary | Assignee | Submitted By | Status | Group | Change Type | Resolution | Pre-applied? | Ballot Resolution | Open Date | Close Date | Last Modified Date
20614 | Add Patient Address and phone number to Patient Profile to meet USCDi Requirements | EH | emhaas | Resolved - Change required | None | Non-substantive | <p>Will add as Must Support. </p> <p> </p> | No | Persuasive | 2019-03-26 | 2019-04-04 | 2019-04-09
20514 | US Core Condition profile conflicts with base spec | EH | mmoseman | Resolved - Change required | None | Non-substantive | <p> </p> <p>Update the US Core profile to be extensible to align with base spec.</p> | None | Persuasive | 2019-03-08 | 2019-03-26 | 2019-03-26
20512 | fix all the spreadsheet generated extension names | EH | emhaas | Resolved - Change required | None | Non-substantive | <p>fix ( note tooling updates may have already resolved this)</p> | None | Persuasive | 2019-03-08 | 2019-03-26 | 2019-04-02
20488 | Update US Core Practitioner to require one slice to be an NPI | EH | lmichaelsen | Resolved - Change required | None | Compatible, substantive | <p>Add text to make it clear that if a system has an NPI for a Practitioner, they must send it.</p> <p>Add a 'must support' slice on the profile. </p> <p> </p> | None | Persuasive | 2019-03-01 | 2019-03-21 | 2019-03-21
20395 | change title and name of US Core Birth Sex Value Set | EH | emhaas | Resolved - Change required | None | Non-substantive | <p>Will remove 'US Core' from the value set name.</p> <p>After the value set is published in VSAC, or in draft state, will include proper OID.</p> | No | Persuasive | 2019-02-14 | 2019-02-28 | 2019-03-04
20330 | diagnostic report summary text is wrong | EH | emhaas | Resolved - Change required | None | Non-substantive | <p>fix text</p> | None | Persuasive | 2019-01-30 | 2019-03-26 | 2019-03-26
20150 | Fix Title of US Core - USCore #184 | GG | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will work with FHIR Product Director to make title more clear.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-09
20149 | Fix Title of US Core - USCore #183 | GG | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will work with FHIR Product Director to make title more clear.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-09
20147 | Merging DocumentReference into single profile - USCore #181 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will merge DocumentReference profile, and keep the DiagnosticReport separate. Will make clear the differences</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-03-28
20146 | New DocumentReference and DiagnosticReport Profiles should be merged into a single DocumentReference and DiagnosticReport Profile - USCore #176 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will merge into a single resource.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20144 | Immunization.statusReason is missing a value set binding. - USCore #171 | GG | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>The binding is inherited from the base Immunization Resource, will see if publishing can pull forward</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20143 | DiagnosticReport.category URL generates "default terminology error display" - USCore #170 | EH | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20142 | Incorrect FHIR version in the hyperlink to the landing page. - USCore #169 | EH | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20141 | Terminology binding naming convention is inconsistent. - USCore #168 | EH | fhir_bot | Resolved - Change required | None | Non-compatible | <p>We will review value sets we control in US Core for consistent naming.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20140 | Change profile name from "Result Observation" to "Laboratory Result Observation" - USCore #167 | EH | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will rename profile to make it clear that it's for Lab Results</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20138 | Typo on conformance statements in CapabilityStatement. - USCore #165 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20137 | Combined the DocumentReference Resources - USCore #160 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will merge and add Category, Author, and Custodian as Must Support. Will make clear how this supports clinical notes</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-09
20129 | Add support for searching condition by category and status - USCore #152 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Add optional search guidance for code and date</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20126 | Updated Condition Category codes to Extensible - USCore #149 | EH | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will update - this is a technical correction</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20125 | Provide source EHR instance identifiers to allow de-duplication when the same EHR data is used to provide data across multiple FHIR resources with overlapping scope. - USCore #148 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will work with commenter to add guidance on the benefit of including identifiers for de-duplication for MedicationStatement and MedicationRequest.</p> <p>Support will be noted as a SHOULD</p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-14 | 2019-03-14
20123 | Support search by context.period - USCore #146 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will update DocumentReference.context.period to 'Must Support'</p> <p> </p> | None | Persuasive | 2019-01-15 | 2019-03-26 | 2019-04-02
20122 | Add status and date search parameters to Immunization - USCore #145 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add search parameters date +lt,+gt and status</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20121 | Add seach by status - USCore #144 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add search by status as recommended ( SHOULD ) as well as combination searches with other search parameters ( SHOULD )</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20120 | Enumerate required search paramters rather than specific combinations of search parameters - USCore #143 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Make it clear in the profiles the searches enumeraated are the base expectations on what a FHIR server supports.</p> <p>Add new search parameters page that servers WILL support additional query combinations and that implementers should submit combination proposals for consideration in future updates.</p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-21 | 2019-02-21
20118 | Add multi-valued search parameters where applicable - USCore #141 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Combinations that the guide requires are helpful to the implementation community. The other combinations are ok and will be added as SHOULD in the CapabilityStatement</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20117 | Add ability to search by code + date - USCore #140 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will add ability to serach by code + date</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20116 | Update name from Argonaut to US Core - USCore #139 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20115 | Fix broken link - USCore #138 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20114 | Merge "original" and "new" FHIR profiles for DiagnosticReport and DocumentReference, or better distinguish them - USCore #137 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will merge DocumentReference (GF#19889)</p> <p>Will keep DiagnosticReport seperate (GF#19888)</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-28 | 2019-02-28
20113 | Add active status for Goal search - USCore #136 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20111 | Did the guide mean to include all of LOINC - USCore #134 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Thank you for asking - we will restrict to CLASSTYPE=LABORATORY</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20110 | Add ServiceRequest - USCore #133 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Develop a place either in the US Core Specfication, the HL7 US Core gitHub repo or another place to track items for future consideration in US Core. </p> <p>Submitters have requirement to suggest recommended procedures and this could be supported ServiceRequest (formerly ProcedureRequest)</p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-21 | 2019-02-21
20107 | Add search parameters to DiagnosticReport - USCore #130 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add search with patient+code+date</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20106 | Broken Links in DiagnosticReport - USCore #129 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20105 | Add search parameters to observation profile - USCore #128 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add search with patient+code+date</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20104 | Rename observations profile to indicate labe only - USCore #127 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>If this remains a stand a lone profile, will rename to make clear Lab only in title and text.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-11
20103 | Add search paramaters to procedure - USCore #126 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add optional search for status and performed</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20101 | Add search parameters to MedicationStatement - USCore #124 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add</p> <p>status to search and effective +gt,lt</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20097 | Add status and date search parameters to MedicationRequest - USCore #120 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add</p> <p>status to search and AuthoredOn (+gt,lt)</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20095 | Typo in US Core Codition Quick Start - USCore #118 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>AutoApproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20092 | Support additional encounter search parameters - USCore #115 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Add support for class and status.</p> <p>Add type search.</p> <p>Add search support for identifier.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-11
20091 | Add Encounter Search by Identifier - USCore #114 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20090 | Fix QICore link - USCore #113 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20089 | Fix reference to CIMI - USCore #112 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>Autoapproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20088 | Value set expansion should be clear more than 2000 concepts - USCore #101 | GG | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Agree this should be fixed, will work with publishing to fix.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20086 | This is the R4 ballot isn't it? - USCore #99 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>We did it solicit comment during this ballot.</p> <p> </p> <p>We plan to merge the DocumentReference profile into one.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-09
20083 | Link not working: http://hl7.org/fhir/us/core-r4/StructureDefinition/us-core-documentreference - this is the link in "Additional mandatory elements inherited from US Core DocumentReference" - USCore #96 | BM | fhir_bot | Resolved - Change required | _Typo | Non-substantive | <p>Autoapproved</p> | None | Persuasive | 2019-01-15 | 2019-02-26 | 2019-02-26
20082 | Should Argonaut be changed to US Core? - USCore #95 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will update to US core</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20081 | Confusion around what the name of the profile is. (Maybe US Core Report/Note DiagnosticReport? Or should this one be US Core Clinical Note Diagnostic Report also? Is it too late to rename US Core DiagnosticReport to "US Core Laboratory DiagnosticReport" t | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will keep DiagnosticReport seperate (GF#19888) and make clear</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-28 | 2019-02-28
20080 | Confusion around what the name of the profile is - I presume it is "Clinical Note DocumentReference"? Make sure that this name is used throughout. Though shouldn't it be something like "US Core Clinical Note DocumentReference"? - USCore #93 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will merge DocumentReference (GF#19889)</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-28 | 2019-02-28
20079 | Clarify the additional date search - USCore #92 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will either explain the date search or update reference to FHIR core (if one exists!)</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20078 | Make client query support of at least one resource mandatory - USCore #91 | EH | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will update to SHALL.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20077 | Fix typo in capability statement - USCore #90 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20076 | Update FHIR Version - USCore #89 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20074 | Update security requirements to reference SMART on FHIR - USCore #87 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will update to reference SMART on FHIR</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20073 | Fix text on security requirements - USCore #86 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-09
20072 | Add Clinical Note Requirements to the CapabilityStatement - USCore #85 | EH | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will add clinical note requirements to the CapabilityStatements when merge them</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-11
20071 | Add search parameters to DocumentReference search - USCore #84 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will add status and category as recommended parameters</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20069 | Update CapabilityStatement to include category - USCore #82 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will update</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20068 | Further explan the docref operation or remove - USCore #81 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will improve guidance and provide some background on why we created. Will update the parameters when merge DocRefereences</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20067 | Further explain the docref operation or remove - USCore #80 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will improve guidance and provide some background on why we created. Will update the parameters when merge DocRefereences</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20066 | Further explan the docref operation or remove - USCore #79 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Add a parameter to $docref to allow client to dictate whether ‘on-demand’ only or both ‘on-demand’ that meet the query parameters and stable documents (or delayed/deferred assembly) that meet the query parameters</p> <p> </p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-04-04 | 2019-04-08
20065 | Add support for Category in DocumentReference - USCore #78 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will update category to 'must support' in DocumentReference when merge them</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20064 | Fix version in CapabilityStatement - USCore #77 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will update</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20062 | Fix search to use category instead of class - USCore #75 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will update quick start search to use category.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20061 | Make Author Required - USCore #74 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will updated Author to required in the profile.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20060 | Fix URI for 'new' Clinical Notes Profile - USCore #73 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will remove new from the profile URI. If the clinical notes profile remains stand alone will include clinical notes in URI</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20059 | Remove other from DocumentReference.category value set - USCore #72 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will remove 'other'</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20057 | Make clear relationship between Clinical Notes profile and existing DocumentReference Profile - USCore #70 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will merge and add Category, Author, and Custodian as Must Support. Will make clear how this supports clinical notes</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20056 | Fix DocumentReference guidance on category - USCore #69 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Fix text to make it clear category is required.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20055 | Typographical or possibly publishing errors in CapabilityStatement profile' - USCore #68 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will fix indicated errors</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20054 | Provide "search" guidance to support MU2015 and medical device-related patient-safety events - USCore #67 | EH | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will inlude additional search criteria.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20053 | Add additional sample resources and sample US-provider-specific profiles derived from the US-Core; show how to reuse US profiles and extensions. - USCore #66 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Thank you for the offer. We would be happy to include additional VA samples that conform to these profiles which will be added to an examples to <a href="https://build.fhir.org/ig/HL7/US-Core-R4/all-examples.html">https://build.fhir.org/ig/HL7/US-Core-R4/all-examples.html</a> and a a note to the profiles where additional examples can be found.</p> <p> </p> <p>Additional derived profiles may be appropriate in the general guidance, or inline, please provide for consideration.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20051 | As examples of profiles derived from US-Core profiles and extensions (e.g. veteran-us-core-patient, us-military-service extension). - USCore #64 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>If the VA and DoD is able to provide such examples we are happy to include in final publication.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20048 | Update DocumentReference Introduction - USCore #61 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>The explanation for including specific elements is included in the introduction of the profile. In this case we missed describing ContentType, we will update the introductory text.</p> <p> </p> <p>Elements that are explicitly profiled (e.g. 'must support', or cardinality change, etc.) are displayed in the differential view.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20047 | Improve names of DiagnosticReport profiles - USCore #60 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will improve the names to make it clear one profile is for LAB, and the other is for DiagnosticReport Clinical Notes.</p> <p> </p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-21 | 2019-02-21
20046 | Improve names of DocumentReference profiles - USCore #59 | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Will merge and add Category, Author, and Custodian as Must Support. Will make clear how this supports clinical notes</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20045 | Clarify support of Argonaut and the CCDS. - USCore #58 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>The general-guidance.html page provides a mapping between the CCDS elements and the US Core profiles.</p> <p>This guide absorbs all prior Argonaut guidance. </p> <p>Will add references to the draft USCDI.</p> <p>Will provide reference link to FHIR core R4 vs R3 vs R2 diff to help implementers see differences arcoss versions. </p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20044 | Change the profile reference and description to match as use for scope of implanted device. - USCore #57 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>see GF#20025</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20043 | It is appropriate to reference the Argonaut project for its seminal work on this suite of profiles, but the work product and requirements are now HL7 committee artifacts and the introductory section should be rewritten to reflect that and the comment. - U | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will update.</p> | None | Persuasive | 2019-01-15 | 2019-02-11 | 2019-02-11
20040 | Align us-core-careplan with CCDS requirements and C-CDA 2.1 and support the health concern addressed by the Care Plan - USCore #53 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>see GF#20034</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20038 | us-core-care plan needs to be harmonized with C-CDA 2.1 - USCore #51 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Please see resolution in GF#20034</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-22
20037 | us-core-care plan does to support "plant of treatment" - USCore #50 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Current design supports a narrative 'plan of treatment' in text. Will make that more clear in the introductory text.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
20036 | us-core-care plan does not reference a Care Team resource - USCore #49 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>See GF#20034</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20035 | Add a Goal profile to support "Care Plan" - us-core-care plan - USCore #48 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>US Core includes a Goal profile. </p> <p>See GF#20034</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20034 | Missing Goals and Instructions in us-core-care plan profile - USCore #47 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Add implementer note that to align with C-CDA:<br /> - US Core Goal SHOULD be present in CarePlan.Goal,<br /> - US Core Condition SHOULD be present in CarePlan.addresses <br /> - Assement and Plan MAY be included as narrative text<br /> </p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20032 | According to the CCDA mapping, the "us-core-device" is actually "US Core Implanted Device Profile"- the name would describe it accurately as "us-core-implanted-device". - USCore #45 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>see GF#20025</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20031 | According to the CCDA mapping, the "us-core-device" is actually "US Core Implanted Device Profile"- the description should describe it accurately. - USCore #44 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>See GF#20025</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20030 | Clarify this profile is intended to provide - primarily - access to the implantable device list managed by an EHR or another type of information system. - USCore #43 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>see GF#20025</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-19 | 2019-03-19
20029 | Add missing "must support" data elements to support the MU2015 and CCDS requirements: (A) Device Identifier; and (B) The following identifiers that compose the Production Identifier: (1) The lot or batch within which a device was manufactured; (2) The ser | BM | fhir_bot | Resolved - Change required | None | Compatible, substantive | <p>Update Device.<strong>udiCarrier.carrierHRF</strong> and Device.<strong>udiCarrier.carrierAIDC </strong>to Must Support</p> <p>Fix introductory text to match (i.e. a UDI string (“udicarrier”) to Device.<strong>udiCarrier.carrierHRF)</strong></p> <p>----</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-07 | 2019-03-14
20028 | Add an "Implant Procedure" profile to describe the context of an implantable device in the required implantable device list. - USCore #41 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>The creation of a specific implant procedure profile is not necessary.</p> <p>Add Implementation note on the use case for Implantable devices. and the 'focalDevice' element can reference a US-Core-Device. which is an implantable device. See GF#20025</p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-07 | 2019-03-07
20027 | Update conformance text for us-device-core to reflect the R3 Device and MU2015 certification criteria. - USCore #40 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will upudate as requested.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-03-07
20025 | The "us-core-device" does not meet the (a)(14) Implantable device list." to the 2015 certification criteria. - USCore #38 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Make it clear the current query will return all devices.</p> <p>Add text referencing (a)(14) Implantable device list.</p> <p>Add recommended (SHOULD) query to support returning by Device.type</p> <p>Implanted devices can be returned by requesting concepts from specific value set -- (Ioana agreed to provide suggested value set for Device.type to return implanted devices by 4/4/2019; should be avialble through SNOMED implantable hierarchy; if unavaible, will publish without this new value set). </p> <p> </p> <p> </p> | None | Persuasive with Mod | 2019-01-15 | 2019-03-07 | 2019-03-07
20024 | either restrict the code to lab codes or expand the category from just 'LAB' - USCore #33 | BM | fhir_bot | Resolved - Change required | None | Non-compatible | <p>Will constrainlLOINC to CLASSTYPE=Laboratory</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20023 | Which is correct- The table or Mandatory Data Elements and Terminology statement? - USCore #32 | BM | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will add 'or text'.</p> <p> </p> <p>Text and Mandatory should align.</p> | None | Persuasive | 2019-01-15 | 2019-02-07 | 2019-02-07
20022 | Clarify Lab Observation Text - USCore #31 | EH | fhir_bot | Resolved - Change required | None | Non-substantive | <p>Will change to </p> <p> Each Observation resource represents an individual laboratory test and result value or component result values, or a “nested” panel (such as a microbial susceptibility panel) which references other observations. They can also be presented in report form or as free text.</p> | None | Persuasive with Mod | 2019-01-15 | 2019-02-07 | 2019-02-07
19946 | Clinical Note text definition should be improved | BM | gdolin | Resolved - Change required | None | Non-substantive | <p>update medical record to health record</p> | None | Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19945 | Clinical Note code misspelled? | BM | gdolin | Resolved - Change required | None | Compatible, substantive | <p>Auto-approved</p> | None | Persuasive | 2019-01-07 | 2019-01-24 | 2019-02-09
19944 | US Core DiagnosticReport Category Codes Value Set - link from codes | BM | gdolin | Resolved - Change required | None | Non-substantive | <p>fix externally links to access LOINC Part codes</p> <p>see <a href="https://chat.fhir.org/#narrow/stream/179202-terminology/topic/LOINC.20Part.20code/near/156815429">https://chat.fhir.org/#narrow/stream/179202-terminology/topic/LOINC.20Part.20code/near/156815429</a></p> <p> </p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-22
19943 | Please merge with Existing US Core DocRef | BM | kboone | Resolved - Change required | None | Compatible, substantive | <p>Will merge DocumentReference profile</p> | None | Persuasive | 2019-01-07 | 2019-01-16 | 2019-02-09
19941 | Change valueset concept listing description to reflect reality. | GG | kboone | Resolved - Change required | None | Non-substantive | <p>The value set contains signifigantly more than 2000 concepts!</p> <p>Will require publishing update.</p> | None | Persuasive | 2019-01-07 | 2019-01-16 | 2019-01-16
19940 | US Core: PractitionerRole shouldn't require code and specialty | EH | mmoseman | Resolved - Change required | None | Compatible, substantive | <p>will update code and specialty to 0..1 and edit the text to reflect this, (Not carried over from STU3)</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-22
19939 | US Core: Encounter.diagnosis shouldn't be must support | EH | mmoseman | Resolved - Change required | None | Non-substantive | <p>Proposal:<br /> - Remove diagnosis, diagnosis.condition and diagnosis.rank as Must Support</p> <p>Add guidance to both the Condition profile and the Encounter profile on how to search for encounter diagnosis </p> <p>Add to Quick Start SHOULD searches. </p> <p> </p> | None | Persuasive with Mod | 2019-01-07 | 2019-03-28 | 2019-03-28
19928 | address.line should have maximum cardinality of 3 | EH | kboone | Resolved - Change required | None | Non-substantive | <p>Will update to 4 to align with C-CDA.</p> <p>Add text that server must support storing upto 4 lines.</p> | None | Persuasive with Mod | 2019-01-07 | 2019-01-16 | 2019-01-16
19927 | Should reflect that preferred identifier scheme for organization is NPI or CLIA identifier for labs | BM | kboone | Resolved - Change required | None | Non-substantive | <p>Add text that NPI or CLIA identifier is preferred identifier for an Organization.</p> <p> </p> <p> </p> | None | Persuasive | 2019-01-07 | 2019-01-16 | 2019-01-16
19926 | Organization.addr | BM | kboone | Resolved - Change required | None | Non-substantive | <p>Will update to Must support 0..1</p> | None | Persuasive | 2019-01-07 | 2019-01-16 | 2019-01-16
19924 | Patient.family should be 0..1 | EH | kboone | Resolved - Change required | None | Compatible, substantive | <p>Will update </p> <p>Family to 0..1 (MUST SUPPORT)<br /> Given to 0..* (MUST SUPPORT)</p> <p>Add invariant that at least one is required (alwasy present).</p> | None | Persuasive with Mod | 2019-01-07 | 2019-01-16 | 2019-01-16
19923 | LOINCDiagnosticReportCodes (extensible) should be constrained for the use case | BM | gdolin | Resolved - Change required | None | Non-substantive | <p>Update the definition to:</p> <p>This value set currently contains all of LOINC. The codes selected should represent discrete and narrative diagnostic observations and reports</p> <p> </p> <p><br /> ---<br /> Future work should be considered to define the 'green box' in the guide (<a href="http://build.fhir.org/ig/HL7/US-Core-R4/clinical-notes-guidance.html">http://build.fhir.org/ig/HL7/US-Core-R4/clinical-notes-guidance.html</a>).</p> | None | Persuasive with Mod | 2019-01-07 | 2019-01-31 | 2019-02-18
19922 | Provide tracing to support understanding of support & compatibility | BM | jlyle | Resolved - Change required | None | Non-substantive | <p>see GF#<a href="http://gforge.hl7.org/gf/project/fhir/tracker/?action=TrackerItemEdit&amp;tracker_item_id=20045">20045</a></p> | None | Persuasive with Mod | 2019-01-07 | 2019-03-26 | 2019-03-26
19921 | US Core Immunization Profile "Text Summary" references deprecated elements | EH | danny_wise | Resolved - Change required | None | Non-substantive | <p>Will make updates to summary page to align with R4 changes.</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19908 | Summary: US Core: Consider using slicing to constrain Results category | EH | cmoesel | Resolved - Change required | None | Non-compatible | <p> Use slicing to constrain the category. </p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19907 | US Core: Inclusion of Practitioner/Endpoint when PractitionerRole is returned | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>Update to make it clear _include support is SHOULD for Practitioner and Endpoint.</p> <p>Remove language:<br /> - The Practitioner resource SHALL be included when returning the PractitionerRole resource.<br /> - The Endpoint resource SHALL be included when returning the PractitionerRole resource.</p> <p> </p> <p>Add an example on how to search with _Include</p> <p> </p> | None | Persuasive with Mod | 2019-01-07 | 2019-03-14 | 2019-03-14
19906 | US Core: Typo in Patient Profile Narrative (quidance -> guidance) | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>Auto-approved</p> | None | Persuasive | 2019-01-07 | 2019-01-23 | 2019-02-09
19905 | US Core: Wrong MedicationRequest Search Format | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>Auto-Approved</p> | None | Persuasive | 2019-01-07 | 2019-01-23 | 2019-01-24
19904 | US Core: Improve Consistency Across Quick Start Sections | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>Make quick start sections consistent across profiles and remove the Response Class statement from Location ( is covered in the CapabilityStatement )</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19903 | US Core: Immunization doesn't have a "flag to indicate whether vaccine was given" | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>update Narrative to reflect changes in underlying profile:</p> <p>reworded to indicate that not-given immunizations should be properly reported via the <em>status</em> attribute.</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19902 | US Core: Goal - search by date is ambiguous | EH | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>Add targetDate 'Must Support'</p> <p>Update query parameter to specify targetDate </p> <p> </p> | None | Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19901 | US Core: DocumentReference date -- mandatory or not? (plus reference to non-existant 'created' field) | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>will clarify that this element is a must support and move text to SHOULD</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19900 | US Core: Diagnostic Report missing constraint for result/presentedForm | BM | cmoesel | Resolved - Change required | None | Non-compatible | <p>Will add invariant</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19899 | US Core: Typo on Condition page ("earch" instead of "Search") | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>Auto-approved</p> | None | Persuasive | 2019-01-07 | 2019-01-24 | 2019-01-28
19898 | US Core: Condition page is rendered without tabbable text/diff/snap/all table | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>This is a technical issue with publishing and will be fixed</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19897 | US Core: Consider using slicing to constrain CarePlan category | EH | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>Change invarient to slice</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19895 | US Core: AllergyIntolerance clinicalStatus - mandatory or not? | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>will add footnote to text to read:</p> <p>"A clnical status of the allergy mandatory unless <em>verificationStatus</em> is '<em>entered-in-error'"</em></p> | None | Not Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19894 | US Core: Wrong attribute in example | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>The \ is a markdown error and will fix</p> <p>the example was for clinicalStatus will update text to reflect.</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19893 | US Core: New DocumentReference author: mandatory or not? | BM | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>Update to 0..*</p> | None | Persuasive with Mod | 2019-01-07 | 2019-03-07 | 2019-03-07
19892 | US Core: TBD / TODO | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>Will provide completed valid examples and text summaries</p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19889 | US Core: new-us-core-documentreference poorly named | BM | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>Will merge the two docrefs and retain the id</p> <p>us-core-documentreference</p> <p>and name </p> <p><a href="https://build.fhir.org/ig/HL7/US-Core-R4/StructureDefinition-us-core-documentreference.html">US Core DocumentReference Profile</a></p> <p>With expanded scope</p> <p> </p> | None | Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19888 | US Core: New US Core DiagnosticReport -independent or merged? | BM | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>Wiil not merge the two DiagnosticReport profiles.</p> <p><a href="https://build.fhir.org/ig/HL7/US-Core-R4/StructureDefinition-new-us-core-diagnosticreport.html">New US Core Diagnostic Report Profile for Report and Note exchange</a> will be renamed to:<br /> </p> <p><a href="https://build.fhir.org/ig/HL7/US-Core-R4/StructureDefinition-new-us-core-diagnosticreport.html">US Core Diagnostic Report Profile for Report and Note exchange</a></p> <p>the id will be renamed from "new-us-core-diagnosticreport"</p> <p>to "us-core-diagnosticreport-note"</p> <p><a href="https://build.fhir.org/ig/HL7/US-Core-R4/StructureDefinition-us-core-diagnosticreport.html">US Core DiagnosticReport Profile</a> will be renamed to</p> <p><a href="https://build.fhir.org/ig/HL7/US-Core-R4/StructureDefinition-us-core-diagnosticreport.html">US Core DiagnosticReport Profile</a> for Laboratory Results Reporting</p> <p>the id will be renamed from </p> <p>"us-core-diagnosticreport:</p> <p>to </p> <p>:"us-core-diagnosticreport-lab"</p> | None | Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19887 | US Core: ValueSet expansion context format | BM | cmoesel | Resolved - Change required | None | Non-substantive | <p>This is not required and will continue to use the shortened</p> <p><em>- <a href="http://hl7.org/fhir/us/core/StructureDefinition/new-us-core-diagnosticreport#DiagnosticReport.category">DiagnosticReport.category</a></em></p> <p><em>- <a href="http://hl7.org/fhir/us/core/StructureDefinition/new-us-core-documentreference#DocumentReference.type">DocumentReference.type</a></em></p> <p><em>- D<a href="http://hl7.org/fhir/us/core/StructureDefinition/new-us-core-documentreference#DocumentReference.class">ocumentReference.class</a></em></p> <p><em>omitting the profile.</em></p> <p>In addition will add <em>DiagnosticReport.codes </em></p> <p> </p> | None | Not Persuasive with Mod | 2019-01-07 | 2019-02-21 | 2019-02-21
19886 | US Core: TODO - link these to LOINC too | BM | cmoesel | Resolved - Change required | None | Compatible, substantive | <p>remove TODO</p> <p>remove Imaging, Pathology, Cardiology (covered further down on page)</p> <p>"In addition, systems are encouraged to support other common notes types such as:</p> <p>Referral note (57133-1)</p> <p> Surgical operation note (11504-8)</p> <p> Nurse Note (34746-8)"</p> <p> </p> | None | Persuasive | 2019-01-07 | 2019-02-21 | 2019-02-21
19872 | DiagnosticReport Requires search by category (Radiology/Cardiology/Pathology). Is this right? | BM | colbyseyferth | Resolved - Change required | None | Non-substantive | <p>Update category search to recommended, consider to make required in future</p> <p>-----<br /> Add to the implementation notes:</p> <p>A server will return how a customer has categorized their reports at a particular site. Categorization of reports is not consistent across sites. (e.g. a system may categorize an orthopedic note as a cardiology.)</p> | None | Persuasive with Mod | 2019-01-04 | 2019-01-31 | 2019-02-18
19854 | US Core: Conformance Requirements for Client Page is 404 | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>will fix</p> | None | Persuasive | 2019-01-03 | 2019-02-21 | 2019-02-21
19853 | US Core: Rendering Issue | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>fix markdown</p> | None | Persuasive | 2019-01-03 | 2019-02-21 | 2019-02-21
19852 | US Core: CarePlan searches over Time Period | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>will add Block-2 "{&amp;date=[date]}" as recommended.</p> | None | Persuasive | 2019-01-03 | 2019-02-21 | 2019-02-21
19851 | USCore: Section Numbering Issue | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>fix section numbering</p> | None | Persuasive | 2019-01-03 | 2019-02-21 | 2019-02-21
19850 | US Core: Patient search on name/gender/birthdate: any 2 or only specific combinations? | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>Will clarify what is supported:</p> <p>name + gender</p> <p>name + birthdate</p> <p>family + gender</p> <p>family + birthdate</p> <p>These are not appropriate and won't be included:</p> <p>given + gender</p> <p>given + birthdate</p> <p>gender + birthdate</p> | None | Persuasive | 2019-01-03 | 2019-02-21 | 2019-02-22
19849 | USCore: jsonesource / xmlesource typos | EH | cmoesel | Resolved - Change required | None | Non-substantive | <p>Auto-approved</p> | None | Persuasive | 2019-01-03 | 2019-01-14 | 2019-01-24
19816 | Clarify the scope of the "US Device" profile to support §170.315(a)(14) Implantable device list requirements | BM | ioana13 | Resolved - Change required | None | Compatible, substantive | <p>see GF#20025</p> | None | Persuasive with Mod | 2018-12-21 | 2019-03-26 | 2019-03-26
19811 | Exclude generic "Ethnicity" code from US Core Detailed Ethnicity value set | EH | rott | Resolved - Change required | None | Non-substantive | <p>this is an abstract grouper code and not intended for use. Will edit the <a href="https://build.fhir.org/ig/HL7/US-Core-R4/CodeSystem-cdcrec.xml.html">cdcrec CodeSystem</a> Definition to mark as <a href="http://build.fhir.org/codesystem.html#status">abstrac</a>t for both the concepts "race" and "ethnicity" </p> | None | Not Persuasive with Mod | 2018-12-19 | 2019-02-21 | 2019-02-21
19810 | Constrain US Core Immunization codes to C-CDA CVX limitations | EH | rott | Resolved - Change required | None | Non-substantive | <p>Will update definition to align with C-CDA and the value set published in VSAC.</p> <p>Update OID to 2.16.840.1.113762.1.4.1010.6 (CVX Vaccines Administered - Vaccine Set)</p> <p>Reach out to publication and Vocabulary about directly pulling value sets from VSAC.</p> | None | Persuasive with Mod | 2018-12-19 | 2019-02-28 | 2019-02-28
19809 | Constrain US Core Smoking Status Observation.status | EH | rott | Resolved - Change required | None | Non-compatible | <p>Will constrain to 'final' and 'entered-in-error'.</p> <p> </p> | None | Persuasive with Mod | 2018-12-19 | 2019-02-28 | 2019-03-01
19793 | Implantable Device list query string is not correct | BM | ioana13 | Resolved - Change required | None | Non-substantive | <p>see GF#20025</p> | None | Persuasive with Mod | 2018-12-18 | 2019-03-26 | 2019-03-26
19792 | Smoking Status representation of eCigarette use | BM | ioana13 | Resolved - Change required | Fit for teleconference | Non-substantive | <p>Change Observation.code to extensible binding on "US Core smoking status value set" which includes the single existing code.</p> <p>Change Observation.valueCodeableConcept to extensible.</p> | None | Persuasive with Mod | 2018-12-18 | 2019-03-21 | 2019-03-21
17803 | Value set definition URLs are broken | GG | rutemartins | Resolved - Change required | None | Non-substantive | <p>Publishing issue, will work with Grahame to fix. </p> | None | Persuasive | 2018-09-05 | 2018-11-15 | 2018-11-15
17679 | Fix Language Value Set Expansion | GG | bamarquard | Resolved - Change required | None | Non-substantive | <p>We definitely want this fixed -- will continue to work with publishing. </p> | None | Persuasive | 2018-08-15 | 2018-11-15 | 2018-11-15
16308 | link does not work | EH | rberge | Resolved - Change required | None | Non-substantive | <p>Auto-approved</p> | None | Persuasive | 2018-05-04 | 2018-05-09 | 2018-05-09
13629 | fix references to provider in MedRequest | EH | emhaas | Resolved - Change required | G | Non-substantive | <p>Auto-approved</p> | None | Persuasive | 2017-07-11 | 2018-07-30 | 2018-08-16
3783 | change value set for us-core-race and us-core-ethnicity | EH | emhaas | Resolved - Change required | None | Compatible, substantive | <p> See #5967</p> | None | Persuasive with Mod | 2014-11-19 | 2015-09-01 | 2017-03-07